## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Karamveer Singh | Week 1 | Duplicate security events found | Sprint 1 | Shubhrangi Tripathy | Logical | Removed duplicates and validated dataset | Week 1 | Closed | Dataset validated
2 | Saraswati Balaso Jadhav | Week 3 | Some features contained inconsistent values | Sprint 3 | Gunjan Munjal | Logical | Applied preprocessing and validation | Week 3 | Closed | Features standardized
3 | Aman Patel | Week 4 | Prediction API returned incorrect field names | Sprint 4 | Rivan Dsilva | Logical | Standardized response schema | Week 4 | Closed | API response verified
4 | Swarada Suraj Deshpande | Week 4 | Dashboard could not display prediction response | Sprint 4 | Varri Ramya | Logical | Updated API mapping | Week 4 | Closed | Integration successful
5 | Arshleen Kaur | Week 5 | Risk score differed for test scenarios | Sprint 5 | Karamveer Singh | Logical | Reviewed risk weights and formula | Week 5 | Closed | Risk calculation validated
6 | Shubhrangi Tripathy | Week 6 | Related events were not grouped correctly | Sprint 6 | Saraswati Balaso Jadhav | Logical | Updated correlation rules | Week 6 | Closed | Correlation validated
7 | Gunjan Munjal | Week 7 | Attack chain visualization had incorrect ordering | Sprint 7 | Aman Patel | User Interface | Corrected event ordering | Week 7 | Closed | Visualization verified
8 | Rivan Dsilva | Week 8 | Minor UI alignment issue | Sprint 8 | Swarada Suraj Deshpande | User Interface | Updated responsive styling | Week 8 | Closed | UI verified

## Sheet2
Logical
User Interface
Maintainability
Standards
Others