## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a security analyst, I want cybersecurity event datasets collected so that security events are available for analysis. | Must | None | Varri Ramya | Completed
Sprint 1 | Sprint 1 | US-02 | As a developer, I want security data cleaned and validated so that unreliable records do not affect analysis. | Must | US-01 | Arshleen Kaur | Completed
Sprint 1 | Sprint 1 | US-03 | As a developer, I want a standardized security event schema so that data from different sources follows a common format. | Must | US-01 | Karamveer Singh | Completed
Sprint 2 | Sprint 2 | US-04 | As a security analyst, I want security events normalized and enriched with threat intelligence so that events contain useful security context. | Must | US-02, US-03 | Shubhrangi Tripathy | Completed
Sprint 2 | Sprint 2 | US-05 | As a security analyst, I want CVE, CVSS and MITRE ATT&CK information mapped to events so that vulnerabilities and attack techniques can be identified. | Should | US-04 | Saraswati Balaso Jadhav | Completed
Sprint 3 | Sprint 3 | US-06 | As a developer, I want security event features prepared so that ML models can process the data. | Must | US-04 | Gunjan Munjal | Completed
Sprint 3 | Sprint 3 | US-07 | As a security analyst, I want anomalous security activities detected automatically so that suspicious events can be identified. | Must | US-06 | Aman Patel | Completed
Sprint 4 | Sprint 4 | US-08 | As a security analyst, I want suspicious events classified with confidence scores so that I can understand the likelihood of a threat. | Must | US-07 | Rivan Dsilva | Completed
Sprint 4 | Sprint 4 | US-09 | As a developer, I want threat predictions stored and exposed through APIs so that frontend applications can consume ML results. | Must | US-08 | Swarada Suraj Deshpande | Completed
Sprint 5 | Sprint 5 | US-10 | As a security analyst, I want risk scores calculated using threat and asset information so that threats can be prioritized. | Must | US-08 | Varri Ramya | Completed
Sprint 5 | Sprint 5 | US-11 | As a security analyst, I want threats categorized by risk level so that critical incidents can be investigated first. | Must | US-10 | Arshleen Kaur | Completed
Sprint 6 | Sprint 6 | US-12 | As a security analyst, I want related security events correlated so that possible attack chains can be identified. | Must | US-10 | Karamveer Singh | Completed
Sprint 6 | Sprint 6 | US-13 | As a security analyst, I want response recommendations generated so that appropriate investigation actions can be suggested. | Should | US-11, US-12 | Shubhrangi Tripathy | Completed
Sprint 7 | Sprint 7 | US-14 | As a security analyst, I want an interactive dashboard so that I can monitor threats and security risks. | Must | US-09, US-11 | Saraswati Balaso Jadhav | Completed
Sprint 7 | Sprint 7 | US-15 | As a security analyst, I want incident details and attack chains displayed so that I can investigate threats efficiently. | Must | US-12 | Gunjan Munjal | Completed
Sprint 8 | Sprint 8 | US-16 | As a security analyst, I want filtering and drill-down capabilities so that I can analyze specific threats and assets. | Should | US-14 | Aman Patel | Completed
Sprint 8 | Sprint 8 | US-17 | As a project team, we want the complete platform tested and documented so that the system is ready for final demonstration. | Must | All previous US | Rivan Dsilva | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours; enter Task Start Date / Task Completion Date with your team's actual dates before submission.
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours)
SPRINT 1 BACKLOG
US-01 | T-001 | Understand project dataset and schema |  |  | Swarada Suraj Deshpande | Analysis | Completed | 4
US-01 | T-002 | Collect/load synthetic SOC dataset |  |  | Varri Ramya | Development | Completed | 5
US-01 | T-003 | Verify security event records |  |  | Arshleen Kaur | Validation | Completed | 4
US-02 | T-004 | Handle missing values |  |  | Karamveer Singh | Data Cleaning | Completed | 5
US-02 | T-005 | Remove duplicate records |  |  | Shubhrangi Tripathy | Data Cleaning | Completed | 4
US-02 | T-006 | Validate data types |  |  | Saraswati Balaso Jadhav | Validation | Completed | 4
US-03 | T-007 | Define standardized schema |  |  | Gunjan Munjal | Design | Completed | 5
US-03 | T-008 | Create normalized dataset |  |  | Aman Patel | Development | Completed | 6
SPRINT 2 BACKLOG
US-04 | T-009 | Normalize security event fields |  |  | Rivan Dsilva | Development | Completed | 6
US-04 | T-010 | Enrich events with security metadata |  |  | Swarada Suraj Deshpande | Development | Completed | 6
US-05 | T-011 | Map CVE information |  |  | Varri Ramya | Enrichment | Completed | 5
US-05 | T-012 | Map CVSS severity |  |  | Arshleen Kaur | Enrichment | Completed | 4
US-05 | T-013 | Map MITRE ATT&CK techniques |  |  | Karamveer Singh | Enrichment | Completed | 6
US-05 | T-014 | Validate enriched records |  |  | Shubhrangi Tripathy | Testing | Completed | 4
US-04 | T-015 | Store processed events in MongoDB |  |  | Saraswati Balaso Jadhav | Database | Completed | 5
SPRINT 3 BACKLOG
US-06 | T-016 | Select ML features |  |  | Gunjan Munjal | Feature Engineering | Completed | 5
US-06 | T-017 | Encode categorical features |  |  | Aman Patel | Preprocessing | Completed | 4
US-06 | T-018 | Scale numerical features |  |  | Rivan Dsilva | Preprocessing | Completed | 4
US-07 | T-019 | Implement Isolation Forest |  |  | Swarada Suraj Deshpande | Model Development | Completed | 6
US-07 | T-020 | Train anomaly detection model |  |  | Varri Ramya | Model Training | Completed | 6
US-07 | T-021 | Generate anomaly scores |  |  | Arshleen Kaur | Prediction | Completed | 4
US-07 | T-022 | Validate anomaly results |  |  | Karamveer Singh | Testing | Completed | 5
SPRINT 4 BACKLOG
US-08 | T-023 | Implement threat classification |  |  | Shubhrangi Tripathy | Development | Completed | 5
US-08 | T-024 | Generate confidence scores |  |  | Saraswati Balaso Jadhav | Development | Completed | 4
US-08 | T-025 | Save trained model |  |  | Gunjan Munjal | Model Management | Completed | 3
US-09 | T-026 | Create prediction API |  |  | Aman Patel | API Development | Completed | 6
US-09 | T-027 | Store predictions in MongoDB |  |  | Rivan Dsilva | Database | Completed | 5
US-09 | T-028 | Test APIs using Postman |  |  | Swarada Suraj Deshpande | Testing | Completed | 4
US-09 | T-029 | Integrate API with frontend |  |  | Varri Ramya | Integration | Completed | 6
SPRINT 5 BACKLOG
US-10 | T-030 | Define risk factors |  |  | Arshleen Kaur | Analysis | Completed | 4
US-10 | T-031 | Define risk scoring formula |  |  | Karamveer Singh | Design | Completed | 5
US-10 | T-032 | Implement risk scoring engine |  |  | Shubhrangi Tripathy | Development | Completed | 7
US-11 | T-033 | Implement risk classification |  |  | Saraswati Balaso Jadhav | Development | Completed | 4
US-11 | T-034 | Implement asset criticality mapping |  |  | Gunjan Munjal | Development | Completed | 5
US-11 | T-035 | Integrate CVSS risk information |  |  | Aman Patel | Integration | Completed | 5
US-10 | T-036 | Validate risk scores |  |  | Rivan Dsilva | Testing | Completed | 5
SPRINT 6 BACKLOG
US-12 | T-037 | Define event correlation rules |  |  | Swarada Suraj Deshpande | Design | Completed | 4
US-12 | T-038 | Correlate events by user/IP/asset |  |  | Varri Ramya | Development | Completed | 7
US-12 | T-039 | Identify possible attack chains |  |  | Arshleen Kaur | Development | Completed | 7
US-13 | T-040 | Define response recommendation rules |  |  | Karamveer Singh | Design | Completed | 4
US-13 | T-041 | Implement recommendations |  |  | Shubhrangi Tripathy | Development | Completed | 6
US-12 | T-042 | Create incident records |  |  | Saraswati Balaso Jadhav | Database | Completed | 5
US-13 | T-043 | Test attack-chain scenarios |  |  | Gunjan Munjal | Testing | Completed | 5
SPRINT 7 BACKLOG
US-14 | T-044 | Design threat dashboard |  |  | Aman Patel | UI Design | Completed | 5
US-14 | T-045 | Create risk KPI cards |  |  | Rivan Dsilva | Development | Completed | 4
US-14 | T-046 | Create threat distribution charts |  |  | Swarada Suraj Deshpande | Development | Completed | 5
US-15 | T-047 | Create incident investigation page |  |  | Varri Ramya | Development | Completed | 7
US-15 | T-048 | Create attack chain visualization |  |  | Arshleen Kaur | Development | Completed | 7
US-14 | T-049 | Integrate risk APIs |  |  | Karamveer Singh | Integration | Completed | 6
SPRINT 8 BACKLOG
US-16 | T-050 | Implement dashboard filters |  |  | Shubhrangi Tripathy | Development | Completed | 5
US-16 | T-051 | Implement drill-down functionality |  |  | Saraswati Balaso Jadhav | Development | Completed | 5
US-17 | T-052 | Perform backend testing |  |  | Gunjan Munjal | Testing | Completed | 6
US-17 | T-053 | Perform frontend testing |  |  | Aman Patel | Testing | Completed | 5
US-17 | T-054 | Perform end-to-end testing |  |  | Rivan Dsilva | Testing | Completed | 7
US-17 | T-055 | Fix identified defects |  |  | Swarada Suraj Deshpande | Bug Fixing | Completed | 6
US-17 | T-056 | Prepare project documentation |  |  | Varri Ramya | Documentation | Completed | 5
US-17 | T-057 | Prepare final presentation/demo |  |  | Arshleen Kaur | Presentation | Completed | 5

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Understanding dataset schema | Discussed schema and clarified required fields
Sprint 1 | Day 2 | Missing values found | Reviewed missing-value handling strategy
Sprint 1 | Day 3 | Duplicate records identified | Removed duplicates and validated records
Sprint 1 | Day 4 | Data type inconsistencies | Standardized data types
Sprint 1 | Day 5 | No major blocker | Continued data validation
Sprint 2 | Day 1 | Enrichment mapping unclear | Discussed CVE and MITRE mapping
Sprint 2 | Day 2 | Some fields required transformation | Applied normalization rules
Sprint 2 | Day 3 | API/database integration issue | Debugged MongoDB connection
Sprint 2 | Day 4 | No major blocker | Continued enrichment
Sprint 2 | Day 5 | Validation issues | Rechecked enriched records
Sprint 3 | Day 1 | Feature selection confusion | Reviewed relevant ML features
Sprint 3 | Day 2 | Categorical encoding issue | Applied appropriate encoding
Sprint 3 | Day 3 | Model parameters required tuning | Tested Isolation Forest parameters
Sprint 3 | Day 4 | Anomaly results required validation | Reviewed sample anomalies
Sprint 3 | Day 5 | No major blocker | Completed model testing
Sprint 4 | Day 1 | Confidence score implementation | Reviewed scoring approach
Sprint 4 | Day 2 | API response structure issue | Standardized JSON response
Sprint 4 | Day 3 | Database storage issue | Fixed prediction repository
Sprint 4 | Day 4 | Frontend API integration issue | Debugged API calls
Sprint 4 | Day 5 | No major blocker | Completed integration
Sprint 5 | Day 1 | Risk factors needed clarification | Defined risk factors
Sprint 5 | Day 2 | Weight selection discussion | Finalized documented weights
Sprint 5 | Day 3 | Risk score validation | Tested multiple scenarios
Sprint 5 | Day 4 | Asset criticality mapping issue | Standardized criticality values
Sprint 5 | Day 5 | No major blocker | Completed risk engine
Sprint 6 | Day 1 | Event correlation logic unclear | Defined correlation rules
Sprint 6 | Day 2 | Multiple events required grouping | Implemented time/user/IP correlation
Sprint 6 | Day 3 | Attack-chain visualization planning | Finalized attack-chain structure
Sprint 6 | Day 4 | Recommendation mapping | Created threat-response mapping
Sprint 6 | Day 5 | No major blocker | Completed security intelligence
Sprint 7 | Day 1 | Dashboard API integration | Connected frontend to APIs
Sprint 7 | Day 2 | Chart data formatting | Updated API response mapping
Sprint 7 | Day 3 | Incident page UI issue | Refined UI components
Sprint 7 | Day 4 | Attack-chain visualization issue | Fixed visualization
Sprint 7 | Day 5 | No major blocker | Completed dashboard integration
Sprint 8 | Day 1 | Minor UI issues | Fixed dashboard issues
Sprint 8 | Day 2 | API edge cases | Added validation
Sprint 8 | Day 3 | E2E testing issues | Fixed identified defects
Sprint 8 | Day 4 | Documentation gaps | Updated documentation
Sprint 8 | Day 5 | No major blocker | Final validation completed

## Retrospection
SL # | Sprint # | Sprint Start | Sprint End | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | Week 1 | Week 1 | Varri Ramya | Validate schema before coding | Assuming all fields are clean | Regular data checks | Added schema validation
2 | Sprint 1 | Week 1 | Week 1 | Arshleen Kaur | Validate schema before coding | Assuming all fields are clean | Regular data checks | Added schema validation
3 | Sprint 1 | Week 1 | Week 1 | Karamveer Singh | Validate schema before coding | Assuming all fields are clean | Regular data checks | Added schema validation
4 | Sprint 1 | Week 1 | Week 1 | Shubhrangi Tripathy | Validate schema before coding | Assuming all fields are clean | Regular data checks | Added schema validation
5 | Sprint 1 | Week 1 | Week 1 | Saraswati Balaso Jadhav | Validate schema before coding | Assuming all fields are clean | Regular data checks | Added schema validation
6 | Sprint 1 | Week 1 | Week 1 | Gunjan Munjal | Validate schema before coding | Assuming all fields are clean | Regular data checks | Added schema validation
7 | Sprint 1 | Week 1 | Week 1 | Aman Patel | Validate schema before coding | Assuming all fields are clean | Regular data checks | Added schema validation
8 | Sprint 1 | Week 1 | Week 1 | Rivan Dsilva | Validate schema before coding | Assuming all fields are clean | Regular data checks | Added schema validation
9 | Sprint 1 | Week 1 | Week 1 | Swarada Suraj Deshpande | Validate schema before coding | Assuming all fields are clean | Regular data checks | Added schema validation
10 | Sprint 2 | Week 2 | Week 2 | Varri Ramya | Document enrichment rules | Manual inconsistent mappings | Data validation | Standardized enrichment rules
11 | Sprint 2 | Week 2 | Week 2 | Arshleen Kaur | Document enrichment rules | Manual inconsistent mappings | Data validation | Standardized enrichment rules
12 | Sprint 2 | Week 2 | Week 2 | Karamveer Singh | Document enrichment rules | Manual inconsistent mappings | Data validation | Standardized enrichment rules
13 | Sprint 2 | Week 2 | Week 2 | Shubhrangi Tripathy | Document enrichment rules | Manual inconsistent mappings | Data validation | Standardized enrichment rules
14 | Sprint 2 | Week 2 | Week 2 | Saraswati Balaso Jadhav | Document enrichment rules | Manual inconsistent mappings | Data validation | Standardized enrichment rules
15 | Sprint 2 | Week 2 | Week 2 | Gunjan Munjal | Document enrichment rules | Manual inconsistent mappings | Data validation | Standardized enrichment rules
16 | Sprint 2 | Week 2 | Week 2 | Aman Patel | Document enrichment rules | Manual inconsistent mappings | Data validation | Standardized enrichment rules
17 | Sprint 2 | Week 2 | Week 2 | Rivan Dsilva | Document enrichment rules | Manual inconsistent mappings | Data validation | Standardized enrichment rules
18 | Sprint 2 | Week 2 | Week 2 | Swarada Suraj Deshpande | Document enrichment rules | Manual inconsistent mappings | Data validation | Standardized enrichment rules
19 | Sprint 3 | Week 3 | Week 3 | Varri Ramya | Test features before training | Using irrelevant features | Experiment tracking | Created feature selection process
20 | Sprint 3 | Week 3 | Week 3 | Arshleen Kaur | Test features before training | Using irrelevant features | Experiment tracking | Created feature selection process
21 | Sprint 3 | Week 3 | Week 3 | Karamveer Singh | Test features before training | Using irrelevant features | Experiment tracking | Created feature selection process
22 | Sprint 3 | Week 3 | Week 3 | Shubhrangi Tripathy | Test features before training | Using irrelevant features | Experiment tracking | Created feature selection process
23 | Sprint 3 | Week 3 | Week 3 | Saraswati Balaso Jadhav | Test features before training | Using irrelevant features | Experiment tracking | Created feature selection process
24 | Sprint 3 | Week 3 | Week 3 | Gunjan Munjal | Test features before training | Using irrelevant features | Experiment tracking | Created feature selection process
25 | Sprint 3 | Week 3 | Week 3 | Aman Patel | Test features before training | Using irrelevant features | Experiment tracking | Created feature selection process
26 | Sprint 3 | Week 3 | Week 3 | Rivan Dsilva | Test features before training | Using irrelevant features | Experiment tracking | Created feature selection process
27 | Sprint 3 | Week 3 | Week 3 | Swarada Suraj Deshpande | Test features before training | Using irrelevant features | Experiment tracking | Created feature selection process
28 | Sprint 4 | Week 4 | Week 4 | Varri Ramya | Define API contracts early | Changing response formats frequently | Postman testing | Standardized API responses
29 | Sprint 4 | Week 4 | Week 4 | Arshleen Kaur | Define API contracts early | Changing response formats frequently | Postman testing | Standardized API responses
30 | Sprint 4 | Week 4 | Week 4 | Karamveer Singh | Define API contracts early | Changing response formats frequently | Postman testing | Standardized API responses
31 | Sprint 4 | Week 4 | Week 4 | Shubhrangi Tripathy | Define API contracts early | Changing response formats frequently | Postman testing | Standardized API responses
32 | Sprint 4 | Week 4 | Week 4 | Saraswati Balaso Jadhav | Define API contracts early | Changing response formats frequently | Postman testing | Standardized API responses
33 | Sprint 4 | Week 4 | Week 4 | Gunjan Munjal | Define API contracts early | Changing response formats frequently | Postman testing | Standardized API responses
34 | Sprint 4 | Week 4 | Week 4 | Aman Patel | Define API contracts early | Changing response formats frequently | Postman testing | Standardized API responses
35 | Sprint 4 | Week 4 | Week 4 | Rivan Dsilva | Define API contracts early | Changing response formats frequently | Postman testing | Standardized API responses
36 | Sprint 4 | Week 4 | Week 4 | Swarada Suraj Deshpande | Define API contracts early | Changing response formats frequently | Postman testing | Standardized API responses
37 | Sprint 5 | Week 5 | Week 5 | Varri Ramya | Validate risk calculations | Hardcoding unexplained values | Scenario-based testing | Added risk validation cases
38 | Sprint 5 | Week 5 | Week 5 | Arshleen Kaur | Validate risk calculations | Hardcoding unexplained values | Scenario-based testing | Added risk validation cases
39 | Sprint 5 | Week 5 | Week 5 | Karamveer Singh | Validate risk calculations | Hardcoding unexplained values | Scenario-based testing | Added risk validation cases
40 | Sprint 5 | Week 5 | Week 5 | Shubhrangi Tripathy | Validate risk calculations | Hardcoding unexplained values | Scenario-based testing | Added risk validation cases
41 | Sprint 5 | Week 5 | Week 5 | Saraswati Balaso Jadhav | Validate risk calculations | Hardcoding unexplained values | Scenario-based testing | Added risk validation cases
42 | Sprint 5 | Week 5 | Week 5 | Gunjan Munjal | Validate risk calculations | Hardcoding unexplained values | Scenario-based testing | Added risk validation cases
43 | Sprint 5 | Week 5 | Week 5 | Aman Patel | Validate risk calculations | Hardcoding unexplained values | Scenario-based testing | Added risk validation cases
44 | Sprint 5 | Week 5 | Week 5 | Rivan Dsilva | Validate risk calculations | Hardcoding unexplained values | Scenario-based testing | Added risk validation cases
45 | Sprint 5 | Week 5 | Week 5 | Swarada Suraj Deshpande | Validate risk calculations | Hardcoding unexplained values | Scenario-based testing | Added risk validation cases
46 | Sprint 6 | Week 6 | Week 6 | Varri Ramya | Design correlation rules first | Building complex logic without testing | Team discussions | Added correlation test cases
47 | Sprint 6 | Week 6 | Week 6 | Arshleen Kaur | Design correlation rules first | Building complex logic without testing | Team discussions | Added correlation test cases
48 | Sprint 6 | Week 6 | Week 6 | Karamveer Singh | Design correlation rules first | Building complex logic without testing | Team discussions | Added correlation test cases
49 | Sprint 6 | Week 6 | Week 6 | Shubhrangi Tripathy | Design correlation rules first | Building complex logic without testing | Team discussions | Added correlation test cases
50 | Sprint 6 | Week 6 | Week 6 | Saraswati Balaso Jadhav | Design correlation rules first | Building complex logic without testing | Team discussions | Added correlation test cases
51 | Sprint 6 | Week 6 | Week 6 | Gunjan Munjal | Design correlation rules first | Building complex logic without testing | Team discussions | Added correlation test cases
52 | Sprint 6 | Week 6 | Week 6 | Aman Patel | Design correlation rules first | Building complex logic without testing | Team discussions | Added correlation test cases
53 | Sprint 6 | Week 6 | Week 6 | Rivan Dsilva | Design correlation rules first | Building complex logic without testing | Team discussions | Added correlation test cases
54 | Sprint 6 | Week 6 | Week 6 | Swarada Suraj Deshpande | Design correlation rules first | Building complex logic without testing | Team discussions | Added correlation test cases
55 | Sprint 7 | Week 7 | Week 7 | Varri Ramya | Integrate APIs early | Waiting until final days for integration | Component-based development | Connected APIs incrementally
56 | Sprint 7 | Week 7 | Week 7 | Arshleen Kaur | Integrate APIs early | Waiting until final days for integration | Component-based development | Connected APIs incrementally
57 | Sprint 7 | Week 7 | Week 7 | Karamveer Singh | Integrate APIs early | Waiting until final days for integration | Component-based development | Connected APIs incrementally
58 | Sprint 7 | Week 7 | Week 7 | Shubhrangi Tripathy | Integrate APIs early | Waiting until final days for integration | Component-based development | Connected APIs incrementally
59 | Sprint 7 | Week 7 | Week 7 | Saraswati Balaso Jadhav | Integrate APIs early | Waiting until final days for integration | Component-based development | Connected APIs incrementally
60 | Sprint 7 | Week 7 | Week 7 | Gunjan Munjal | Integrate APIs early | Waiting until final days for integration | Component-based development | Connected APIs incrementally
61 | Sprint 7 | Week 7 | Week 7 | Aman Patel | Integrate APIs early | Waiting until final days for integration | Component-based development | Connected APIs incrementally
62 | Sprint 7 | Week 7 | Week 7 | Rivan Dsilva | Integrate APIs early | Waiting until final days for integration | Component-based development | Connected APIs incrementally
63 | Sprint 7 | Week 7 | Week 7 | Swarada Suraj Deshpande | Integrate APIs early | Waiting until final days for integration | Component-based development | Connected APIs incrementally
64 | Sprint 8 | Week 8 | Week 8 | Varri Ramya | Perform E2E testing early | Last-minute testing | Peer review | Completed full E2E testing
65 | Sprint 8 | Week 8 | Week 8 | Arshleen Kaur | Perform E2E testing early | Last-minute testing | Peer review | Completed full E2E testing
66 | Sprint 8 | Week 8 | Week 8 | Karamveer Singh | Perform E2E testing early | Last-minute testing | Peer review | Completed full E2E testing
67 | Sprint 8 | Week 8 | Week 8 | Shubhrangi Tripathy | Perform E2E testing early | Last-minute testing | Peer review | Completed full E2E testing
68 | Sprint 8 | Week 8 | Week 8 | Saraswati Balaso Jadhav | Perform E2E testing early | Last-minute testing | Peer review | Completed full E2E testing
69 | Sprint 8 | Week 8 | Week 8 | Gunjan Munjal | Perform E2E testing early | Last-minute testing | Peer review | Completed full E2E testing
70 | Sprint 8 | Week 8 | Week 8 | Aman Patel | Perform E2E testing early | Last-minute testing | Peer review | Completed full E2E testing
71 | Sprint 8 | Week 8 | Week 8 | Rivan Dsilva | Perform E2E testing early | Last-minute testing | Peer review | Completed full E2E testing
72 | Sprint 8 | Week 8 | Week 8 | Swarada Suraj Deshpande | Perform E2E testing early | Last-minute testing | Peer review | Completed full E2E testing